## Slide 1: Electrical Contractors Since 1953
Jared M. Barfield
Vice-President, Carolinas Division

## Slide 2
Based Out Of: Mableton, GA
Local Office: Charlotte, NC
Current No. Of Employees: 240 Over Four States
2019 FY Earnings: $80MM+
Coverage Area: Georgia, Alabama, Florida, Tennessee, South Carolina, and North Carolina
Company Overview

## Slide 3
What are we here to talk about?
Runway Lighting
  Threshold
  Centerline
  Edge
  Touchdown Zone (TDZ)
  Takeoff Hold Lighting (THL’s)
Taxiway Lighting
  Centerline
  Edge
  Guard
  Stop Bar
  Runway Entrance Lights (REL’s)
Airfield Guidance Signs

## Slide 4
Normal Airfield Lighting Installation Phases
General Contractor established sub grade and sub base.
Lighting centerlines laid out.
Conduit Installed

## Slide 5
Normal Airfield Lighting Installation Phases
Light Bases Installed (If PCC Pavement)
Pavement Placed

## Slide 6
Light Bases Cored and Placed (If in Shoulder Pavement.
Wire and Transformers Installed.
Normal Airfield Lighting Installation Phases

## Slide 7
Spacers, Rings, and Fixtures Installed.
System Terminated, Tested, and Energized.
Sealing.
Normal Airfield Lighting Installation Phases

## Slide 8
Normal Airfield Lighting Installation Phases
Airfield Guidance Signs

## Slide 9
Common Issues Facing an Electrical Contractor
Joint Conflicts Between Light Cans and PCC Pavement Joints

## Slide 10
Common Issues Facing an Electrical Contractor
Survey
Prompt, Accurate Survey is Critical To Installation.
FAA Advisory Circular 150/5340-30D
Top of Fixture Edge Must Be +0 and -1/16” From Pavement Surface.
Required Aim Tolerance (Azimuth) +/- 1/2 Degree

## Slide 11
Common Issues Facing an Electrical Contractor
Paving Accuracy
Small Variations In Paving Can Mean Costly Repairs
Repairs Include Spacer Rings, Tapered Rings, Removal And Replacement of the Base Can, or Complete Slab Removal.
Workmanship
Having a well trained workforce with the proper materials and tooling for the task is critical.

## Slide 12
Common Issues Facing an Electrical Contractor
Other Issues:
Adequate Time For Installation of Electrical Work
Coordination With Paving Operations
Small Batch Concrete
Material Procurement (Steel Products)
Damage to Completed Work

## Slide 13
Success Stories

## Slide 14
Success Stories

## Slide 15
Success Stories

## Slide 16
Project Highlights

## Slide 17
Project Highlights
I-285 Bridge Structures
Hartsfield-Jackson International Airport
Taxiway N&S Bridge Construction
Charlotte Douglas International Airport

## Slide 18
Oooops…